## Fee Breakdown
		Approach (A)		Approach (B)		Approach (C)
%	Phase	% Const. Costs	Not-To-Exceed	% Const. Costs	Not-To-Exceed	% Const. Costs	Not-To-Exceed

5.00%	Phase 1: / Programming	0.4%	$169	0.4%	$191	0.5%	$225
15.00%	Phase 2: / Schematic Design / (Drawings for Plan Commission Meeting)	1.1%	$506	1.3%	$574	1.5%	$675
20.00%	Phase 3: / Design Development	1.5%	$675	1.7%	$765	2.0%	$900
35.00%	Phase 4: / Construction Documents	2.6%	$1,181	3.0%	$1,339	3.5%	$1,575
5.00%	Phase 5: / Bidding & Contract Negotiation	0.4%	$169	0.4%	$191	0.5%	$225
20.00%	Phase 6: / Construction Administration	1.5%	$675	1.7%	$765	2.0%	$900

100.00%	All Phases	7.5%	$3,375	8.5%	$3,825	10.0%	$4,500
Assuming a Construction Cost =							$45,000

## Hour Breakdown
	Square Footage - Existing	1,500 SF
	Dollar per Square Footage	30 $/SF
	Total Estimated Construction Costs	$45,000.00
	Architecture Fees - Percentage of Construction	7.5%
	Architecture Fees	$3,375.00
	Fee per Square Foot	2.25

	Percentage of Time	100%
Everyone’s Time – Averaged	Average Billing Rate ($/Hr)	$47.00
			Each Phase	Cumulative	Hours dedicated to each phase	Weeks – ¼ person		Weeks – ½ person		Weeks – ¾ person		weeks - 1 person		weeks - 1.5 person		weeks - 2 people
	Phase 1 - Programming	5.00%	$168.75	$168.75	4 hrs	0.4 wks	1.8 days	0.2 wks	0.9 days	0.1 wks	0.6 days	0.1 wks	0.4 days	0.1 wks	0.3 days	0.0 wks	0.2 days
	Phase 2 - Schematic	15.00%	$506.25	$675.00	11 hrs	1.1 wks	5.4 days	0.5 wks	2.7 days	0.4 wks	1.8 days	0.3 wks	1.3 days	0.2 wks	0.9 days	0.1 wks	0.6 days
	Phase 3 - Design Development	20.00%	$675.00	$1,350.00	14 hrs	1.4 wks	7.2 days	0.7 wks	3.6 days	0.5 wks	2.4 days	0.4 wks	1.8 days	0.2 wks	1.2 days	0.2 wks	0.8 days
	Phase 4 - Construction Documents	35.00%	$1,181.25	$2,531.25	25 hrs	2.5 wks	12.6 days	1.3 wks	6.3 days	0.8 wks	4.2 days	0.6 wks	3.1 days	0.4 wks	2.1 days	0.3 wks	1.3 days
	Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$168.75	$2,700.00	4 hrs	0.4 wks	1.8 days	0.2 wks	0.9 days	0.1 wks	0.6 days	0.1 wks	0.4 days	0.1 wks	0.3 days	0.0 wks	0.2 days
	Phase 6 - Construction Administration	20.00%	$675.00	$3,375.00	14 hrs	1.4 wks	7.2 days	0.7 wks	3.6 days	0.5 wks	2.4 days	0.4 wks	1.8 days	0.2 wks	1.2 days	0.2 wks	0.8 days
		100.00%	$3,375.00	$3,375.00	72 hrs	7.2 wks	35.9 days	3.6 wks	18.0 days	2.4 wks	12.0 days	1.8 wks	9.0 days	1.2 wks	6.0 days	0.9 wks	3.8 days

Individual Breakdowns Below

Regis’ Time	Percentage of Time	60%
	Billing Rate ($/Hr)	$35.00
			Each Phase	Cumulative	Hours dedicated to each phase	Weeks – ¼ person		Weeks – ½ person		Weeks – ¾ person		weeks - 1 person		weeks - 1.5 person		weeks - 2 people
	Phase 1 - Programming	5.00%	$101.25	$101.25	3 hrs	0.3 wks	1.4 days	0.1 wks	0.7 days	0.1 wks	0.5 days	0.1 wks	0.4 days	0.0 wks	0.2 days	0.0 wks	0.1 days
	Phase 2 - Schematic	15.00%	$303.75	$405.00	9 hrs	0.9 wks	4.3 days	0.4 wks	2.2 days	0.3 wks	1.4 days	0.2 wks	1.1 days	0.1 wks	0.7 days	0.1 wks	0.4 days
	Phase 3 - Design Development	20.00%	$405.00	$810.00	12 hrs	1.2 wks	5.8 days	0.6 wks	2.9 days	0.4 wks	1.9 days	0.3 wks	1.4 days	0.2 wks	1.0 days	0.1 wks	0.6 days
	Phase 4 - Construction Documents	35.00%	$708.75	$1,518.75	20 hrs	2.0 wks	10.1 days	1.0 wks	5.1 days	0.7 wks	3.4 days	0.5 wks	2.5 days	0.3 wks	1.7 days	0.3 wks	1.0 days
	Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$101.25	$1,620.00	3 hrs	0.3 wks	1.4 days	0.1 wks	0.7 days	0.1 wks	0.5 days	0.1 wks	0.4 days	0.0 wks	0.2 days	0.0 wks	0.1 days
	Phase 6 - Construction Administration	20.00%	$405.00	$2,025.00	12 hrs	1.2 wks	5.8 days	0.6 wks	2.9 days	0.4 wks	1.9 days	0.3 wks	1.4 days	0.2 wks	1.0 days	0.1 wks	0.6 days
		100.00%	$2,025.00	$2,025.00	43 hrs	5.8 wks	28.9 days	2.9 wks	14.5 days	1.9 wks	9.6 days	1.4 wks	7.2 days	1.0 wks	4.8 days	0.7 wks	2.9 days

Ryan’s Time	Percentage of Time	20%
	Billing Rate ($/Hr)	$75.00
			Each Phase	Cumulative	Hours dedicated to each phase	Weeks – ¼ person		Weeks – ½ person		Weeks – ¾ person		weeks - 1 person		weeks - 1.5 person		weeks - 2 people
	Phase 1 - Programming	5.00%	$101.25	$101.25	1 hrs	0.1 wks	0.7 days	0.1 wks	0.3 days	0.0 wks	0.2 days	0.0 wks	0.2 days	0.0 wks	0.1 days	0.0 wks	0.1 days
	Phase 2 - Schematic	15.00%	$303.75	$405.00	4 hrs	0.4 wks	2.0 days	0.2 wks	1.0 days	0.1 wks	0.7 days	0.1 wks	0.5 days	0.1 wks	0.3 days	0.1 wks	0.3 days
	Phase 3 - Design Development	20.00%	$405.00	$810.00	5 hrs	0.5 wks	2.7 days	0.3 wks	1.4 days	0.2 wks	0.9 days	0.1 wks	0.7 days	0.1 wks	0.5 days	0.1 wks	0.3 days
	Phase 4 - Construction Documents	35.00%	$708.75	$1,518.75	9 hrs	0.9 wks	4.7 days	0.5 wks	2.4 days	0.3 wks	1.6 days	0.2 wks	1.2 days	0.2 wks	0.8 days	0.1 wks	0.6 days
	Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$101.25	$1,620.00	1 hrs	0.1 wks	0.7 days	0.1 wks	0.3 days	0.0 wks	0.2 days	0.0 wks	0.2 days	0.0 wks	0.1 days	0.0 wks	0.1 days
	Phase 6 - Construction Administration	20.00%	$405.00	$2,025.00	5 hrs	0.5 wks	2.7 days	0.3 wks	1.4 days	0.2 wks	0.9 days	0.1 wks	0.7 days	0.1 wks	0.5 days	0.1 wks	0.3 days
		100.00%	$675.00	$675.00	14 hrs	2.7 wks	13.5 days	1.4 wks	6.8 days	0.9 wks	4.5 days	0.7 wks	3.4 days	0.5 wks	2.3 days	0.3 wks	1.7 days

Tim’s Time	Percentage of Time	20%
	Billing Rate ($/Hr)	$55.00
			Each Phase	Cumulative	Hours dedicated to each phase	Weeks – ¼ person		Weeks – ½ person		Weeks – ¾ person		weeks - 1 person		weeks - 1.5 person		weeks - 2 people
	Phase 1 - Programming	5.00%	$101.25	$101.25	2 hrs	0.2 wks	0.9 days	0.1 wks	0.5 days	0.1 wks	0.3 days	0.0 wks	0.2 days	0.0 wks	0.2 days	0.0 wks	0.1 days
	Phase 2 - Schematic	15.00%	$303.75	$405.00	6 hrs	0.6 wks	2.8 days	0.3 wks	1.4 days	0.2 wks	0.9 days	0.1 wks	0.7 days	0.1 wks	0.5 days	0.1 wks	0.3 days
	Phase 3 - Design Development	20.00%	$405.00	$810.00	7 hrs	0.7 wks	3.7 days	0.4 wks	1.8 days	0.2 wks	1.2 days	0.2 wks	0.9 days	0.1 wks	0.6 days	0.1 wks	0.5 days
	Phase 4 - Construction Documents	35.00%	$708.75	$1,518.75	13 hrs	1.3 wks	6.4 days	0.6 wks	3.2 days	0.4 wks	2.1 days	0.3 wks	1.6 days	0.2 wks	1.1 days	0.2 wks	0.8 days
	Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$101.25	$1,620.00	2 hrs	0.2 wks	0.9 days	0.1 wks	0.5 days	0.1 wks	0.3 days	0.0 wks	0.2 days	0.0 wks	0.2 days	0.0 wks	0.1 days
	Phase 6 - Construction Administration	20.00%	$405.00	$2,025.00	7 hrs	0.7 wks	3.7 days	0.4 wks	1.8 days	0.2 wks	1.2 days	0.2 wks	0.9 days	0.1 wks	0.6 days	0.1 wks	0.5 days
		100.00%	$675.00	$675.00	14 hrs	3.7 wks	18.4 days	1.8 wks	9.2 days	1.2 wks	6.1 days	0.9 wks	4.6 days	0.6 wks	3.1 days	0.5 wks	2.3 days