## Fee Breakdown
		Approach (A)		Approach (B)		Approach (C)
%	Phase	% Const. Costs	Not-To-Exceed	% Const. Costs	Not-To-Exceed	% Const. Costs	Not-To-Exceed

5.00%	Phase 1: / Programming	0.4%	$253	0.4%	$287	0.5%	$338
15.00%	Phase 2: / Schematic Design / (Drawings for Plan Commission Meeting)	1.1%	$759	1.3%	$861	1.5%	$1,013
20.00%	Phase 3: / Design Development	1.5%	$1,013	1.7%	$1,148	2.0%	$1,350
35.00%	Phase 4: / Construction Documents	2.6%	$1,772	3.0%	$2,008	3.5%	$2,363
5.00%	Phase 5: / Bidding & Contract Negotiation	0.4%	$253	0.4%	$287	0.5%	$338
20.00%	Phase 6: / Construction Administration	1.5%	$1,013	1.7%	$1,148	2.0%	$1,350

100.00%	All Phases	7.5%	$5,063	8.5%	$5,738	10.0%	$6,750
Assuming a Construction Cost =							$67,500

## Hour Breakdown
	Square Footage - Existing	1,500 SF
	Dollar per Square Footage	45 $/SF
	Total Estimated Construction Costs	$67,500.00
	Architecture Fees - Percentage of Construction	7.5%
	Architecture Fees	$5,062.50
	Architecture Fee per Square Foot	3.38

	Percentage of Time	100%
Everyone’s Time – Averaged	Average Billing Rate ($/Hr)	$47.00
			Each Phase	Cumulative	Hours dedicated to each phase	Weeks – ¼ person		Weeks – ½ person		Weeks – ¾ person		weeks - 1 person		weeks - 1.5 person		weeks - 2 people
	Phase 1 - Programming	5.00%	$253.13	$253.13	5 hrs	0.5 wks	2.7 days	0.3 wks	1.3 days	0.2 wks	0.9 days	0.1 wks	0.7 days	0.1 wks	0.4 days	0.1 wks	0.3 days
	Phase 2 - Schematic	15.00%	$759.38	$1,012.50	16 hrs	1.6 wks	8.1 days	0.8 wks	4.0 days	0.5 wks	2.7 days	0.4 wks	2.0 days	0.3 wks	1.3 days	0.2 wks	1.0 days
	Phase 3 - Design Development	20.00%	$1,012.50	$2,025.00	22 hrs	2.2 wks	10.8 days	1.1 wks	5.4 days	0.7 wks	3.6 days	0.5 wks	2.7 days	0.4 wks	1.8 days	0.3 wks	1.3 days
	Phase 4 - Construction Documents	35.00%	$1,771.88	$3,796.88	38 hrs	3.8 wks	18.8 days	1.9 wks	9.4 days	1.3 wks	6.3 days	0.9 wks	4.7 days	0.6 wks	3.1 days	0.5 wks	2.4 days
	Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$253.13	$4,050.00	5 hrs	0.5 wks	2.7 days	0.3 wks	1.3 days	0.2 wks	0.9 days	0.1 wks	0.7 days	0.1 wks	0.4 days	0.1 wks	0.3 days
	Phase 6 - Construction Administration	20.00%	$1,012.50	$5,062.50	22 hrs	2.2 wks	10.8 days	1.1 wks	5.4 days	0.7 wks	3.6 days	0.5 wks	2.7 days	0.4 wks	1.8 days	0.3 wks	1.3 days
		100.00%	$5,062.50	$5,062.50	108 hrs	10.8 wks	53.9 days	5.4 wks	26.9 days	3.6 wks	18.0 days	2.7 wks	13.5 days	1.8 wks	9.0 days	1.3 wks	6.7 days

Individual Breakdowns Below

Regis’ Time	Percentage of Time	60%
	Billing Rate ($/Hr)	$35.00
			Each Phase	Cumulative	Hours dedicated to each phase	Weeks – ¼ person		Weeks – ½ person		Weeks – ¾ person		weeks - 1 person		weeks - 1.5 person		weeks - 2 people
	Phase 1 - Programming	5.00%	$151.88	$151.88	4 hrs	0.4 wks	2.2 days	0.2 wks	1.1 days	0.1 wks	0.7 days	0.1 wks	0.5 days	0.1 wks	0.4 days	0.1 wks	0.3 days
	Phase 2 - Schematic	15.00%	$455.63	$607.50	13 hrs	1.3 wks	6.5 days	0.7 wks	3.3 days	0.4 wks	2.2 days	0.3 wks	1.6 days	0.2 wks	1.1 days	0.2 wks	0.8 days
	Phase 3 - Design Development	20.00%	$607.50	$1,215.00	17 hrs	1.7 wks	8.7 days	0.9 wks	4.3 days	0.6 wks	2.9 days	0.4 wks	2.2 days	0.3 wks	1.4 days	0.2 wks	1.1 days
	Phase 4 - Construction Documents	35.00%	$1,063.13	$2,278.13	30 hrs	3.0 wks	15.2 days	1.5 wks	7.6 days	1.0 wks	5.1 days	0.8 wks	3.8 days	0.5 wks	2.5 days	0.4 wks	1.9 days
	Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$151.88	$2,430.00	4 hrs	0.4 wks	2.2 days	0.2 wks	1.1 days	0.1 wks	0.7 days	0.1 wks	0.5 days	0.1 wks	0.4 days	0.1 wks	0.3 days
	Phase 6 - Construction Administration	20.00%	$607.50	$3,037.50	17 hrs	1.7 wks	8.7 days	0.9 wks	4.3 days	0.6 wks	2.9 days	0.4 wks	2.2 days	0.3 wks	1.4 days	0.2 wks	1.1 days
		100.00%	$3,037.50	$3,037.50	65 hrs	8.7 wks	43.4 days	4.3 wks	21.7 days	2.9 wks	14.5 days	2.2 wks	10.8 days	1.4 wks	7.2 days	1.1 wks	5.4 days

Ryan’s Time	Percentage of Time	20%
	Billing Rate ($/Hr)	$75.00
			Each Phase	Cumulative	Hours dedicated to each phase	Weeks – ¼ person		Weeks – ½ person		Weeks – ¾ person		weeks - 1 person		weeks - 1.5 person		weeks - 2 people
	Phase 1 - Programming	5.00%	$151.88	$151.88	2 hrs	0.2 wks	1.0 days	0.1 wks	0.5 days	0.1 wks	0.3 days	0.1 wks	0.3 days	0.0 wks	0.2 days	0.0 wks	0.1 days
	Phase 2 - Schematic	15.00%	$455.63	$607.50	6 hrs	0.6 wks	3.0 days	0.3 wks	1.5 days	0.2 wks	1.0 days	0.2 wks	0.8 days	0.1 wks	0.5 days	0.1 wks	0.4 days
	Phase 3 - Design Development	20.00%	$607.50	$1,215.00	8 hrs	0.8 wks	4.1 days	0.4 wks	2.0 days	0.3 wks	1.4 days	0.2 wks	1.0 days	0.1 wks	0.7 days	0.1 wks	0.5 days
	Phase 4 - Construction Documents	35.00%	$1,063.13	$2,278.13	14 hrs	1.4 wks	7.1 days	0.7 wks	3.5 days	0.5 wks	2.4 days	0.4 wks	1.8 days	0.2 wks	1.2 days	0.2 wks	0.9 days
	Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$151.88	$2,430.00	2 hrs	0.2 wks	1.0 days	0.1 wks	0.5 days	0.1 wks	0.3 days	0.1 wks	0.3 days	0.0 wks	0.2 days	0.0 wks	0.1 days
	Phase 6 - Construction Administration	20.00%	$607.50	$3,037.50	8 hrs	0.8 wks	4.1 days	0.4 wks	2.0 days	0.3 wks	1.4 days	0.2 wks	1.0 days	0.1 wks	0.7 days	0.1 wks	0.5 days
		100.00%	$1,012.50	$1,012.50	22 hrs	4.1 wks	20.3 days	2.0 wks	10.1 days	1.4 wks	6.8 days	1.0 wks	5.1 days	0.7 wks	3.4 days	0.5 wks	2.5 days

Tim’s Time	Percentage of Time	20%
	Billing Rate ($/Hr)	$55.00
			Each Phase	Cumulative	Hours dedicated to each phase	Weeks – ¼ person		Weeks – ½ person		Weeks – ¾ person		weeks - 1 person		weeks - 1.5 person		weeks - 2 people
	Phase 1 - Programming	5.00%	$151.88	$151.88	3 hrs	0.3 wks	1.4 days	0.1 wks	0.7 days	0.1 wks	0.5 days	0.1 wks	0.3 days	0.0 wks	0.2 days	0.0 wks	0.2 days
	Phase 2 - Schematic	15.00%	$455.63	$607.50	8 hrs	0.8 wks	4.1 days	0.4 wks	2.1 days	0.3 wks	1.4 days	0.2 wks	1.0 days	0.1 wks	0.7 days	0.1 wks	0.5 days
	Phase 3 - Design Development	20.00%	$607.50	$1,215.00	11 hrs	1.1 wks	5.5 days	0.6 wks	2.8 days	0.4 wks	1.8 days	0.3 wks	1.4 days	0.2 wks	0.9 days	0.1 wks	0.7 days
	Phase 4 - Construction Documents	35.00%	$1,063.13	$2,278.13	19 hrs	1.9 wks	9.7 days	1.0 wks	4.8 days	0.6 wks	3.2 days	0.5 wks	2.4 days	0.3 wks	1.6 days	0.2 wks	1.2 days
	Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$151.88	$2,430.00	3 hrs	0.3 wks	1.4 days	0.1 wks	0.7 days	0.1 wks	0.5 days	0.1 wks	0.3 days	0.0 wks	0.2 days	0.0 wks	0.2 days
	Phase 6 - Construction Administration	20.00%	$607.50	$3,037.50	11 hrs	1.1 wks	5.5 days	0.6 wks	2.8 days	0.4 wks	1.8 days	0.3 wks	1.4 days	0.2 wks	0.9 days	0.1 wks	0.7 days
		100.00%	$1,012.50	$1,012.50	22 hrs	5.5 wks	27.6 days	2.8 wks	13.8 days	1.8 wks	9.2 days	1.4 wks	6.9 days	0.9 wks	4.6 days	0.7 wks	3.5 days